LEVEL 10 MEETING NOTES

Second Team  ·  April 9, 2026  ·  Kuchai  ·  ~5:00 PM

1. SEGUE

Quick personal/professional wins shared to open the meeting. (Not captured in transcript — standard 5-min check-in.)

2. SCORECARD

No formal scorecard defined yet — first L10. Scorecard to be established at April 14 L10 once metrics are agreed.

NOTE — Scorecard TBD Agreed to define tracked metrics at the April 14 L10. See To-Do #7 below.

3. ROCK REVIEW — Q2 2026 (SET THIS MEETING)

No prior rocks to review — this is the founding L10. Rocks below were SET during this meeting and are effective as of April 9, 2026.

| # | ROCK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1 | Lock V/TO and publish to Notion War Room | Adrian | On Track |
| 2 | Build Content Agent MVP — runs both founders' content end-to-end | Adrian | On Track |
| 3 | Build Sales Agent MVP (pro services + B2B distribution variants) | Adrian | On Track |
| 4 | Build Finance Agent MVP (with Autocount integration) | Adrian | On Track |
| 5 | Personal brand content strategy + daily posting cadence | Both | On Track |
| 6 | Brand blueprint workshop (positioning, differentiation, messaging) | Both | On Track |
| 7 | Jayson learns core AI tools (Claude/Paperclip) to guide UX | Jayson | On Track |
| 8 | Define v0.1 product scope + master company context file strategy | Adrian | On Track |

Rock Ownership Note Rocks 2–4 (agent builds) are sequenced one-per-month: Content Agent by end April, Sales Agent by end May, Finance Agent by end June. Each rock owner is Adrian as lead builder; Jayson feeds business context and reviews UX.

4. HEADLINES (CUSTOMER / EMPLOYEE / OTHER NEWS)

Business Updates

- Intercom's FIN (AI customer service agent) is already at $100M ARR on outcome-based pricing — this validates the AI-agent-as-a-product model. CS agent category is now crowded; we deprioritize it.

- Competitor observed building in public without launching product yet — funded, AI-as-a-service model, targeting December launch. Signals market is moving but window remains open.

- Jayson's existing tech already has an Autocount API connector — this accelerates the Finance Agent build significantly.

Founder Updates

- Adrian: replacing human editor with AI editor; letting go of current video editor. Will handle YouTube with AI + one editor for final polish.

- Jayson: committed to Kuchai on Tuesdays, Thursdays, Fridays. Will stay later on Tuesdays for L10 sessions.

5. TO-DO LIST (7-DAY ACTIONS)

Due by: Tuesday April 14, 2026 L10 @ 5pm, Kuchai. Status: OPEN = not started, DONE = complete.

|  | TO-DO | OWNER | DUE |
| --- | --- | --- | --- |
| OPEN | Adrian sends V/TO document to Jayson for review | Adrian | Apr 10 |
| OPEN | Jayson populates Notion War Room with V/TO content | Jayson | Apr 14 |
| OPEN | Adrian: draft full Content Agent architecture/structure — ready to present at Apr 14 L10 | Adrian | Apr 14 |
| OPEN | Jayson: build personal brand content strategy — topics, content pillars, cadence, platform | Jayson | Apr 14 |
| OPEN | Adrian: build personal brand content strategy — YouTube, LinkedIn, X, cadence | Adrian | Apr 14 |
| OPEN | Both founders: start posting content NOW — do NOT wait for agent (B-roll + text is fine) | Both | Apr 10 |
| OPEN | Both founders: define metrics/scorecard for tracking at L10 — bring proposal to Apr 14 | Both | Apr 14 |
| OPEN | Jayson: begin learning Claude and/or Paperclip basics ahead of Apr 14 | Jayson | Apr 14 |
| OPEN | Schedule brand blueprint workshop date within Q2 | Both | Apr 14 |
| OPEN | Adrian: begin defining v0.1 product scope and master company context file strategy | Adrian | Apr 14 |

6. ISSUES — IDS (IDENTIFY · DISCUSS · SOLVE)

Issues discussed and decisions reached in this meeting. Open issues move to the Issues List for future L10 IDS.

DECISIONS MADE (CLOSED THIS MEETING)

| # | ISSUE | OWNER | RESOLUTION / STATUS |
| --- | --- | --- | --- |
| 1 | Strategic filter: what governs every business decision we make? | Both | DECIDED: 6-criteria Sovereign Business Filter locked — scalable, location-independent, async by design, low marginal cost, leverage-based, AI-native. Filter is permanent. Done-for-you consulting, live cohorts, human-led selling all fail the filter and are OFF the table in Year 1. |
| 2 | Core values: what drives how we work and decide? | Both | DECIDED: 5 values confirmed — Growth Mindset, Extreme Ownership, Bias to Action, Results Not Effort, + 5th value (working: Experimenters Not Builders). 5th value wording to be finalised at Apr 14 L10. |
| 3 | Core focus: what is the one-line purpose of Second Team? | Both | DECIDED: direction confirmed — 'AI operating system for owner-led businesses.' Exact phrase to be simplified into a single clean sentence before Apr 14. |
| 4 | Time horizon for BHAG: 10-year or 5-year target? | Both | DECIDED: Compress to 5-year BHAG. 10-year horizon is too uncertain given AI velocity. BHAG: $100M ARR by April 2031 (~10,000 subscribers @ ~$800/month average). |
| 5 | Growth formula: how do we stage our revenue targets? | Both | DECIDED: 33322 ladder — Y1: $1M → Y2: $3M → Y3: $9M → Y4: $27M → Y5: $54M+ (to $100M). First year target of $1M ARR is the anchor. Stretch: Y3 at $10M is feasible. |
| 6 | Marketing strategy: what are our four channels? | Both | DECIDED: Content (build-in-public), SEO/GEO, Partnerships/Affiliates/Cross-collab, Paid Ads (last, not until Q4 at earliest). |
| 7 | Agent architecture: one agent per function or one department with sub-agents? | Both | DECIDED: One department = multiple specialized sub-agents. e.g., Content Agent = YouTube sub-agent + LinkedIn sub-agent + scriptwriter sub-agent. Better training, better results, less context bleed. |
| 8 | Agent roadmap: which agents to build in 2026, in what order? | Both | DECIDED: Focus on THREE only — Content Agent (April), Sales Agent (May), Finance Agent (June). Ops and Customer Service explicitly deprioritized — Ops too complex; CS dominated by Intercom FIN. |
| 9 | Sales Agent: one variant or two? | Both | DECIDED: Two variants — professional services (Adrian's agency context) first, then B2B distribution (Jayson's context). Jayson to map his full sales process and feed to Adrian. |
| 10 | Finance Agent: what is the anchor integration? | Both | DECIDED: Autocount API connector (Jayson's existing tech). Finance Agent covers invoicing, collections, cash flow, margin tracking, P&L automation. Potentially sellable separately to Autocount users. |
| 11 | 1-Year Plan structure: how do we stage the year? | Both | DECIDED: 4 phases — Phase 1 (Apr–May): Content Agent + build-in-public launch. Phase 2 (June): Sales Agent. Phase 3 (Jul–Sep): Finance Agent + beta testers. Phase 4 (Oct–Dec): soft launch, limited seats, full public launch on Product Hunt/HN in December. |
| 12 | Content start date: when do both founders start posting? | Both | DECIDED: Immediately — do not wait for the Content Agent. B-roll and text is enough. Adrian: daily. Jayson: 3×/week minimum. Agent is a productivity multiplier, not a prerequisite. |
| 13 | Platform for content agent (initial): Claude, Paperclip, or other? | Adrian | DECIDED (provisional): Likely Claude or Paperclip for V1 — not a polished SaaS yet. Will be an agent system both founders can use directly. Decision on final platform pending Adrian's April architecture work. |
| 14 | ICP targeting approach for initial launch? | Both | DECIDED: Start with two founder-owned verticals — professional services (Adrian: agency) and B2B distribution/trading (Jayson). Higher tech-maturity clients are priority first. Low tech-maturity (paper-based, no systems) are harder and deprioritized for launch. |
| 15 | Master company context file: should it be platform-agnostic? | Both | DECIDED: Yes — all company context and knowledge must be stored in a portable, platform-agnostic master file. LLMs change; our data should not be hostage to any one platform. This is a foundational architecture decision. |
| 16 | L10 cadence: when and where do we meet? | Both | DECIDED: Every Tuesday, 5pm, in person at Kuchai. Jayson to stay later on Tuesdays. First official cadence L10: April 14, 2026. |

OPEN ISSUES — CARRY TO ISSUES LIST

These were raised but not fully resolved. Each requires IDS at a future L10.

| # | ISSUE | OWNER | RESOLUTION / STATUS |
| --- | --- | --- | --- |
| I1 | 5th core value: final wording. Options: 'Experimenters Not Builders,' 'Unreasonable Ambition,' 'Think Billions Not Millions,' or other. Jayson's concern: does it capture billion-dollar ambition vs. just million-dollar building? | Both | — Open — |
| I2 | Bootstrap only vs. raise capital? $100M in 5 years may require external funding for paid acquisition scale. Both founders open to raising but no decision made. | Both | — Open — |
| I3 | Single product vs. platform + agent marketplace from Day 1? Current leaning: single product first. Marketplace model is a future-state option. | Both | — Open — |
| I4 | Pricing and tier structure. Current placeholder: $499/$999/$1,999 three-tier. Needs beta signal before locking. Actual price point TBD — should reflect 'cost of a part-time employee.' | Both | — Open — |
| I5 | Equity, vesting, and founder compensation structure specific to Second Team (separate from existing businesses). | Both | — Open — |
| I6 | Metrics for public transparency reporting — what do we publish vs. keep private? | Both | — Open — |
| I7 | Open-source strategy: do we open-source parts of Second Team (agent SDK, context layer) to accelerate distribution and defensibility? | Both | — Open — |
| I8 | Policy for inbound consulting/services revenue — working recommendation is hard no (filter violation), but not formally ratified. | Both | — Open — |

7. CONCLUDE — RATINGS & NEXT STEPS

| Meeting Rating | Not formally rated (founding L10 — process still being established) |
| --- | --- |
| Next L10 | Tuesday, April 14, 2026 @ 5:00 PM — Kuchai (in person) |
| Adrian brings | Content Agent architecture/structure; personal brand content strategy; V/TO sent to Jayson |
| Jayson brings | Personal brand content strategy; Notion War Room populated with V/TO; thoughts on brand blueprint workshop timing |
| Both decide at Apr 14 | Final wording of 5th core value; scorecard metrics; next priority after content agent |
| Meeting Duration | ~63 min (L10) + ~54 min (impromptu Google Meet follow-up) = ~2h 17min total |
| Attendees | Adrian Ching (Upstack Studio), Jayson Phang |
| Facilitator | Adrian |

This Was a Founding L10 — Not a Typical Weekly Meeting Most of this session was V/TO alignment and strategy — not standard L10 cadence. The 16 decisions above are now locked in the V/TO. Starting April 14, the L10 format runs in full: Segue → Scorecard → Rock Review → Headlines → To-Do → IDS → Conclude. Keep it to 90 minutes.

— Second Team L10 · April 9, 2026 · Kuchai —